## Sheet1
| Task | Subtask | Estimation In hours | Actual time
1 | Create a fake DB/in-memory-data service |  | 2 | 1.5
2 | Create models/classes/planning the app arhitecture |  | 2 | 1.5
3 | Create the data service |  | 1 | 1
4 | List View | HTML/CSS | 3
Front-end-logic (subtasks below)
|  | HTML Requests | 1 | 0.5
|  | Pgination | 3
|  | Sort functionality | 5
5 | Product Card | add to cart functionality | 4
6 | Product Details | HTML/CSS | 1
|  | add to card functionality | 2
7 | Shopping cart | HTML/CSS | 2
Front-end-logic (subtasks below)
|  | select quantity | 2
|  | total price | 2
|  | place order | 2
8 | Login functionality (pana aici m-a ajutat norocul ) |  | 6
9 | order page | HTML/CSS | 2
|  | Front-end-logic | 6
| buffer | 30% | 13.8
| Total |  | 59.8